## wbs
Developing an E-Learning Platform
Project Initiation
Platform Architecture
Course Management
Student Management
Assessment Management
Integration and Testing
Deployment and Launch
Maintanance and Support
Define Project Scope
Identify stakeholders and requirements
Create Project Charter
Design Platform Structure
Choose Technology Stack
Setup development environment
Course creation functionality
Course Enrollment and Management
Instructor Tools
Integration of all modules
User acceptance testing (UAT)
Bug fixing and Perfomance optimization
User Profiles and Accounts
Progress Tracking and Reporting
Communication Tools
Set assessment deadlines
Evaluation and Grading
Perfomance Anlystics
Prepare deployment environment
Launch strategy and rollout plan
User training and onboarding
Establish support channels
Monitor platform perfomance
Implement updates
Define Course Structure
User registration
Grading and Feedback
Profile Management
Generate Progress report
Design assessment
Automated grading
Analystics dashboard
KEY:
Major Task -
Sub-Task -
Activity -

## GanttChart
Gantt Chart of e-learning platform |  |  |  | PROJECT CALENDER (DAYS)
Task / Activity | Duration | Start Date | End Date | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
Define project scope | 6 days | 17/7/2024 | 22/7/2024
Identify stakeholders | 6 days | 22/7/2024 | 27/7/2024
Create project charter | 5 days | 27/7/2024 | 2024-01-08
Design overall platform structure | 7 days | 2024-01-08 | 2024-08-08
Choose technology stack | 7 days | 2024-08-08 | 14/8/2024
Set up development environment | 8 days | 15/8/2024 | 23/8/2024
Define course structure | 3 days | 23/8/2024 | 25/8/2024
Implement course content upload | 4 days | 25/8/2024 | 28/8/2024
User registration and authentication | 7 days | 28/8/2024 | 2024-04-09
Enrollment management | 7 days | 2024-04-09 | 2024-11-09
Dashboard for instructors | 8 days | 2024-11-09 | 19/9/2024
Grading and feedback system | 7 days | 19/9/2024 | 26/9/2024
Student registration process | 5 days | 26/9/2024 | 2024-01-10
Profile management | 5 days | 2024-02-10 | 2024-06-10
Track course progress | 10 days | 2024-08-10 | 2024-12-10
Generate progress reports | 3 days | 13/10/2024 | 15/10/2024
Messaging system | 7 days | 15/10/2024 | 21/10/2024
Design assessment types | 5 days | 21/10/2024 | 25/10/2024
Set assessment deadlines | 5 days | 25/10/2024 | 30/10/2024
Automated grading | 4 days | 2024-01-11 | 2024-04-11
Manual grading interface | 3 days | 2024-05-11 | 2024-07-11
Analytics dashboard | 6 days | 2024-08-11 | 13/11/2024
Identify trends and student perfomance | 3 days | 13/11/2024 | 15/11/2024
Integration of all modules | 10 days | 16/11/2024 | 25/11/2024
User acceptance testing (UAT) | 6 days | 25/11/2024 | 30/11/2024
Bug fixing and performance optimization | 7 days | 2024-01-12 | 2024-07-12
Prepare deployment environment | 8 days | 2024-07-12 | 14/12/2024
Launch strategy and rollout plan | 7 days | 14/12/2024 | 20/12/2024
User training and onboarding | 7 days | 2025-01-01 | 2025-07-01
Establish support channels | 7 days | 2025-08-01 | 14/1/2025
Monitor platform performance | 7 days | 16/1/2025 | 22/1/2025
Implement updates and enhancements | 7 days | 22/1/2025 | 28/1/2025
KEY:
JULY -
AUGUST -
SEPTEMBER -
OCTOBER -
NOVEMBER -
DECEMBER -
JANUARY -